## Sheet1
research | 80 hrs - ish
set up env
retrofit start
logging
start docs
accounts
OAuth2
albums
| estimate | april 3 actuals | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07
comments | 6 | 5
custom gallery | 8 | 7
gallery | 16 |  | 9 | 9 | 5
image | 16
conversation | 6 |  |  |  |  | 3
notification | 4
memegen | 2
topic | 4
clean up docs | 4
do logo | 4
do site | 8
TOTAL | 78